## Sheet1
| Task | Hours to complete | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Uday | Individual schedule | 2
| Requirement collection | 3
| System design | 5
| Database setup | 3
| main menu and pause menu development | 5
| HUD and inventory system development | 5
| save and load functionality | 5
| settings menu and preferences | 2
| programming | 10
| testing | 4
| user documentaion | 2
| final integration and bug fixing | 3
| installation and deployment | 3
Subtotal
| Task | Hours to complete | spent(hrs)
Braydyn | Individual schedule | 2
| Requirement collection | 4
| room design and layout | 6
| object and enemy spawn point logic | 8
| procedural stitching generation programming | 10
| error handlers implementation | 4
| testing and debugging | 4
| optimization | 6
| documentation | 4
subtotal
| Task | Hours to complete | spent(hrs)
Tavin | 1. Plan Boss fight details | 5
| 2. Program Boss | 17
| 3. Program environment | 4
| 4. Create sprites and animations for boss | 8
| 5. Create sprites and animations for environment | 7
| 6. Add in enemies made by enemy designer. | 1
| 7. Testing and balancing | 6
| Task | Hours to complete | spent(hrs)
Dax | 1. Design item shop level | 2
| 2. Program random shop item generator | 2
| 3. Design and create item shop UI | 3
| 4. Program item shop | 5
| 5. Plan items for item shop | 5
| 6. Create item sprites, animations, and attributes. | 30
| 7. Testing and debugging | 5
Zach | Tasks | Hours to complete | spent(hrs)
| 1. XP table mapping | 2 | bar: 1 to 3
| 2. Upgrade Drafting | 3 | bar: 1 to 4
| 3. XP UI | 2 | bar: 3 to 4
| 4. Upgrades UI | 3 | bar: 5 to 7
| 5. Upgrade Integration in Unity | 8 | bar: 8 to 15
| 6. Compatibility Testing | 4 | bar: 16 to 19
| 7. Error Documentation and Fixing | 6 | bar: 20 to 25
| 8. Artwork | 4 | bar: 5 to 32
Gabe | Task | Hours to complete | spent(hrs)
| Brainstorm various enemies | 2
| Make enemy class | 4
| create various enemy type classes | 24
| sprites, animation and sound | 20
| snemy balancing | 4
| stress testing | 4
| documentation | 3
Liam | task | Hours to complete | spent(hrs)
| predefine workload | 2
| collaboration between members | 3
| organization of git files | 3
| character design + theme design | 8
| documentation and revision | 6
| programming and haptic integration + mobile | 16
| testing features and capability of mobile devices | 4
| Install and integration | 4